## How to Use
M&E System Setup Toolkit
A Practical Template for NGOs and CSR Teams
Based on: Monitoring & Evaluation Systems for Development Projects
About This Template
This workbook provides a structured, ready-to-use template for setting up a Monitoring and Evaluation (M&E) system for any development project. It follows an 8-step process — from defining your Theory of Change to establishing learning and review mechanisms.
How to Use
Step 1: Start with the 'Theory of Change' sheet — map your project's change pathway
Step 2: Move to 'Logical Framework' — define SMART indicators at input, output, outcome and impact levels
Step 3: Fill in 'Baselines & Targets' — establish your starting point and desired change
Step 4: Complete the 'Data Collection Plan' — define what, how, who and when for each indicator
Step 5: Set up 'Dashboard KPIs' — identify your key tracking metrics
Step 6: Plan your 'M&E Budget' — allocate resources for monitoring and evaluation activities
Step 7: Use the 'Data Quality' sheet — build quality assurance mechanisms
Step 8: Design your 'Learning & Review' process — create a structured review calendar
Colour Coding
Grey rows = Example/sample entries for reference (delete and replace with your project details)
Yellow cells = Input cells (fill in your project-specific information)
Blue headers = Column headers
Green cells = Computed or summary cells
Illustrative Project Used in Examples
All sample entries use a hypothetical 'Integrated Rural Development Program' covering education, health & nutrition, skill development, women's empowerment and community institutions across 5 villages in a tribal block. Replace these with your own project details.
Note
This template is designed to be adaptable. Add or remove rows as needed. Each sheet can be used independently or as part of a complete M&E system setup.
For support in designing or strengthening your M&E systems, connect with us at www.transunifyy.com or write to contact@transunifyy.com

## 1. Theory of Change
Step 1: Theory of Change — Map your project's change pathway
Instructions: Define the problem your project addresses, then map the logical chain from activities to long-term impact. List key assumptions that must hold true for the change to occur. Grey rows are illustrative examples — replace with your project details.
Problem / Need | Activities / Interventions | Outputs | Outcomes (Short-Medium Term) | Long-term Impact | Assumptions / Risks
High dropout rates among tribal children (grades 6-8); only 38% complete secondary school | Establish 5 remedial learning centres; train 15 community tutors; provide learning kits; conduct parent engagement workshops | 5 learning centres operational; 250 children enrolled; 15 tutors trained; 10 parent meetings conducted per village | Attendance improves from 62% to 85%; learning outcomes improve by 20%; parents actively support children's education | Improved secondary school completion rates; reduced inter-generational poverty; better employability | Government schools remain operational; no major migration during school year; trained tutors stay engaged
High prevalence of malnutrition among children under 5 (42% stunted); limited WASH practices | Growth monitoring camps; nutrition counselling for mothers; kitchen garden support for 200 HHs; WASH awareness drives in schools and villages | 12 growth monitoring camps/year; 200 mothers counselled; 200 kitchen gardens established; 5 school WASH sessions | 30% reduction in underweight children; 60% HHs adopt improved dietary practices; 70% HHs practise handwashing with soap | Reduced child malnutrition and stunting rates; improved maternal and child health outcomes | Anganwadi workers remain active; fresh produce available year-round from kitchen gardens; WASH infrastructure maintained
Limited livelihood options for women; 85% dependent on seasonal agricultural labour; no savings culture | Form 20 SHGs; financial literacy training for 300 women; skill training (tailoring, food processing); micro-enterprise seed grants | 20 SHGs formed (300 members); 300 women trained; 50 micro-enterprises seeded; ₹15 lakh savings mobilised | 60% women report increased income; 70% have active savings; 40 micro-enterprises sustainable; reduced dependence on moneylenders | Women's economic empowerment; improved intra-household decision-making; self-sustaining SHG ecosystem | Market demand exists for products/services; SHGs maintain financial discipline; no major economic shock

## 2. Logical Framework
Step 2: Logical Framework — Define SMART indicators at each results level
Instructions: For each thematic area, define indicators at Input, Output, Outcome and Impact levels. Ensure indicators are Specific, Measurable, Achievable, Relevant and Time-bound (SMART). Grey rows are illustrative — replace with your indicators.
Thematic Area | Level | Indicator | Definition / Description | Unit | Baseline Value | Midline Target | Endline Target | Data Source | Frequency | Responsible Person
Education | Input | No. of remedial learning centres established | Functional learning centres with trained tutors, space and materials | Number | 0 | 5 | 5 | Centre register / Field visit | Annual | Education Lead
Education | Output | No. of children enrolled in remedial centres | Children aged 6-14 attending at least 3 sessions/week | Number | 0 | 200 | 250 | Attendance registers | Monthly | Education Lead
Education | Outcome | % improvement in grade-appropriate learning levels | % children achieving grade-level competency in reading and math (ASER tool) | Percentage | 34% | 55% | 70% | Learning assessment | Annual | M&E Coordinator
Education | Impact | Secondary school completion rate | % enrolled children completing secondary school in project villages | Percentage | 38% | 50% | 65% | School records + HH survey | Endline | M& E/ Programme Director

## 3. Baselines & Targets
Step 3: Baselines and Targets — Establish starting points and desired outcomes
Instructions: For each indicator, record the baseline value and source. Set progressive targets aligned with your LFA. Update 'Actual' column periodically. Grey rows are illustrative.
Indicator | Baseline Value | Baseline Date | Baseline Source | Year 1 Target | Year 2 Target (Midline) | Year 3 Target | Year 5 Target (Endline) | Actual (Current) | % Achieved vs Midline | Remarks
No. of children enrolled in remedial centres | 0 | Apr 2024 | Project inception report | 150 | 200 | 230 | 250
% children at grade-level competency | 34% | Apr 2024 | ASER-based assessment | 40% | 55% | 62% | 70%
Secondary school completion rate | 38% | Apr 2024 | School records | 42% | 50% | 58% | 65% |  |  | Long-term indicator

## 4. Data Collection Plan
Step 4: Data Collection Plan — Define what, how, who and when for each indicator
Instructions: For each indicator, specify the data collection method, tool, frequency and responsible person. Include ethical safeguards. Grey rows are illustrative.
Indicator | Data Collection Method | Tool / Instrument | Sample Size | Frequency | Responsible Person | Data Storage | Quality Check | Ethical Considerations
Children enrolled in remedial centres | Attendance register review | Monthly attendance sheet (standardised format) | All enrolled children (census) | Monthly | Education Lead | Project MIS / Excel tracker | Spot-check 2 centres/month | Parental consent for child participation
Learning level improvement | Learning assessment (ASER tool) | ASER-based reading and math test | All enrolled children | Annual (pre-post) | M&E Coordinator + Tutors | Assessment database | External assessor for 20% sample | Age-appropriate, non-threatening format; results not used punitively

## 5. Dashboard KPIs
Step 5: Dashboard KPIs — Key performance indicators for real-time tracking
Instructions: Identify 15-20 key metrics for decision-makers. Update 'Actual' at each reporting cycle. Status: On Track / At Risk / Off Track. Grey rows are illustrative.
KPI Category | KPI Name | Unit | Target | Actual | % Achievement | Status | Reporting Frequency | Data Source
Reach | Total beneficiary HHs covered | Number | 500 |  |  |  | Monthly | Beneficiary register
Reach | Total direct beneficiaries (individuals) | Number | 2500 |  |  |  | Quarterly | Programme MIS
Education | Children enrolled in remedial centres | Number | 250 |  |  |  | Monthly | Attendance register
Education | % children at grade-level competency | Percentage | 55% |  |  |  | Annual | Learning assessment
Compliance | No. of field monitoring visits conducted | Number | 24 |  |  |  | Monthly | Visit reports

## 6. M&E Budget
Step 6: M&E Budget — Allocate resources for monitoring and evaluation
Instructions: Budget for M&E as an integral project function (typically 5-10% of total project budget). Include assessments, field monitoring, technology, training and third-party evaluations. Grey rows are illustrative.
Budget Line Item | Description | Unit | Qty | Unit Cost (₹) | Total Cost (₹) | Funding Source | Timeline
Baseline Assessment | External baseline study covering all thematic areas across 5 villages | Study | 1 | 250000 | 250000 | Project Budget | Month 1-2
Midline Evaluation | Third-party midline evaluation with HH survey + qualitative methods | Study | 1 | 400000 | 400000 | Project Budget | Year 2-3
Endline Evaluation | Third-party endline evaluation and impact assessment | Study | 1 | 500000 | 500000 | Project Budget | Year 5
M&E Coordinator (Annual) | Dedicated M&E staff to manage data collection, analysis and reporting | Person-Year | 3 | 480000 | 1440000 | Project Budget | Year 1-3
Data Collection (Surveys) | Enumerator costs for HH surveys, FGDs and community assessments | Rounds | 3 | 120000 | 360000 | Project Budget | Baseline / Mid / End
Monthly Field Monitoring | Monthly field visits by programme team for process monitoring | Visits/Year | 3 | 120000 | 360000 | Project Budget | Year 1-3 (monthly)
Dashboard & Technology | Project MIS setup, data platform and dashboard development | Lump Sum | 1 | 150000 | 150000 | Project Budget | Year 1
Capacity Building | Training of field staff on M&E tools, data collection and data quality | Trainings | 6 | 20000 | 120000 | Project Budget | Bi-annual
Data Quality Audits | Periodic data quality reviews and third-party spot checks | Audits | 4 | 40000 | 160000 | Project Budget | Bi-annual
Documentation & Reporting | Report design, case studies, printing and dissemination | Reports | 6 | 15000 | 90000 | Project Budget | Bi-annual
Learning & Review Workshops | Quarterly stakeholder review meetings and annual learning events | Events | 12 | 10000 | 120000 | Project Budget | Quarterly
TOTAL M&E BUDGET |  |  |  |  | 3950000
Tip: M&E budget should typically be 5-10% of total project budget. Projects with multiple locations, complex interventions or donor reporting requirements may need higher allocation.

## 7. Data Quality
Step 7: Data Quality Assurance — Build mechanisms for reliable data
Instructions: Use this checklist to assess and strengthen data quality across your M&E system. Review periodically (quarterly recommended). Status: Y = Yes / N = No / P = Partial.
Quality Dimension | Checklist Item | Status (Y/N/P) | Evidence / Remarks | Responsible | Review Date
Validity | Are all indicators clearly defined with written measurement protocols?
Validity | Do data collection tools measure what they intend to measure (face validity)?
Validity | Are tools pre-tested / piloted before field deployment?
Reliability | Are standard operating procedures (SOPs) documented for all data collection methods?
Reliability | Are enumerators / data collectors trained on tool administration and protocols?
Reliability | Is inter-rater reliability tested for subjective or qualitative indicators?
Timeliness | Is data collected and reported within defined timeframes?
Timeliness | Are mechanisms in place for flagging delayed data submission?
Completeness | Are all required data fields captured for each record?
Completeness | Is there a documented process for handling missing or incomplete data?
Completeness | Are non-response rates tracked and reasons documented?
Accuracy | Is supervisor field verification conducted on a sample of records (minimum 10%)?
Accuracy | Are data entry validation rules applied (range checks, skip logic, mandatory fields)?
Accuracy | Is triangulation used to cross-verify key findings across methods?
Consistency | Are indicator definitions and measurement methods consistent across time periods?
Consistency | Are any changes in methodology documented with rationale and impact assessment?
Confidentiality | Is informed consent obtained from all participants before data collection?
Confidentiality | Is personally identifiable information stored securely with restricted access?
Confidentiality | Are data access and sharing protocols defined and enforced?
Documentation | Are raw data files systematically archived with version control?
Documentation | Is there a data dictionary defining all variables, codes and categories?
Documentation | Are data quality audit findings documented and acted upon with timelines?

## 8. Learning & Review
Step 8: Learning & Review Mechanisms — Create a structured review calendar
Instructions: Design a review calendar that generates insights and improves programme effectiveness. The real value of M&E lies in learning, not just reporting. Grey rows are illustrative.
Review Type | Frequency | Participants | Key Questions to Ask | Documentation Format | Follow-up Mechanism | Next Review Date
Weekly Field Check-in | Weekly | Programme team + Field staff | What activities were completed this week? Any implementation bottlenecks? Are beneficiaries participating as expected? Any safety or ethical concerns? | Brief notes / shared tracker | Action items assigned to individuals with deadlines
Monthly Progress Review | Monthly | Programme Director + Thematic Leads + M&E Coordinator | Are we on track against monthly milestones? What is the fund utilisation status? Are data collection schedules being met? Any quality concerns from field visits? | Monthly progress report + Dashboard screenshot | Decisions documented in MoM; follow-up tracked in next review
Quarterly Stakeholder Review | Quarterly | CSR/Funder + NGO Leadership + Programme Team + Community Reps | What outputs and outcomes are emerging? Are targets being met? What corrective actions are needed? What are the key learnings? Are community voices being heard? | Quarterly report with KPI dashboard + photos + case studies | Formal MoM with action plan; revised timelines if needed
Annual Strategic Review | Annual | Board / Trustees + Programme Director + External Evaluator if any | What is cumulative progress? Are we on track for long-term impact? What strategic shifts are needed? What worked well and what didn't? Should any interventions be scaled or discontinued? | Annual report + Evaluation findings + Financial summary | Strategic recommendations; revised LFA targets; budget reallocation
Midline / Endline Evaluation | As per M&E plan | External Evaluator + Programme Team + Community | What has changed since baseline? Can changes be attributed to the programme? What are unintended effects? What should be scaled or discontinued? | Evaluation report + Management response + Dissemination brief | Management response with action plan and timelines